## Executive Summary
Universal Sompo AI Claim Evidence Finder — Excel Build Plan
Structured Excel conversion of the 4-week build plan: scope, timeline, architecture, requirements, GPU/cloud cost and delivery controls.
Dashboard View
Pilot duration | 4 weeks / 20 working days |  | Daily volume assumption | 20–50 complaints/day | Evidence turnaround target | 60–90 sec
Compressed pilot delivery window |  |  | 3–5 concurrent investigators |  | Per complaint evidence discovery
Default infra stance | API-first / no GPU |  | Manual search reduction target | ≥70% | Top-3 relevance precision target | ≥80%
Add GPU only for self-hosted inference |  |  | Measured against current RCU workflow |  | After ranking calibration
Build Objective
Deliver a usable evidence assistant in 4 weeks: extract claim facts, search public news/web/image sources, rank evidence, flag mismatches, and generate investigator-ready outputs with audit trail. The tool assists RCU; it does not make final fraud decisions.
Scope pillar | What is delivered | Excel tracking view |  | Decision Discipline
Input normalization | FIR + Quest fields converted into structured accident object | Schema + mandatory fields + confidence gate |  | If Quest integration or search vendor approval is delayed in Week 1, proceed with secure CSV/manual upload and a pre-approved search API fallback. Pilot momentum is more important than waiting for perfect integration.
Evidence discovery | Multiple queries across news, web and image-source matches | Search integration + dedupe + metadata table
Mismatch scoring | Cause/date/location/vehicle/entity consistency flags | Weighted scoring model + calibration notes
Output packaging | Investigator report with top links, score, rationale and export | Excel/PDF pack + audit log + UAT output

## 4-Week Timeline
4-Week Delivery Plan — Week-by-Week Output
Each week ends with a demo, test cases and measurable handoff.
Week | Workstream | Deadline | Committed Output | Acceptance Criteria | Primary Dependency | Fallback | Owner / Reviewer
W1 | Discovery + ingestion | Day 5 | Quest export/API path frozen; claim schema and mandatory fields defined; FIR OCR/text extraction MVP; human review screen for extracted facts. | Minimum fields extracted with confidence score; reviewer can correct facts before search; sample cases loaded. | Quest field access, FIR samples, RCU acceptance criteria. | Secure CSV/manual upload using provided fields. | Build team + RCU reviewer
W2 | Search engine | Day 10 | Query generator live; news/web/image search integrations; async fetch and URL dedupe; evidence metadata stored. | 5–8 queries per case; duplicate URLs removed; source/date/snippet/query-used captured. | Approved search API vendor and source whitelist. | Use one approved vendor first; add others after pilot. | Backend + RCU reviewer
W3 | Scoring + report | Day 15 | Weighted relevance score; mismatch flags by cause/date/location; Excel/PDF evidence pack; audit log of query and source. | Top evidence visible with rationale; mismatch flags explainable; export generated for sample cases. | Historical cases + expected findings for calibration. | Manual threshold calibration on 25–50 cases. | AI/backend + RCU reviewer
W4 | UAT + deployment | Day 20 | Test on 25–50 historical cases; ranking calibration with RCU; cloud/on-prem deployment package; tech docs and handover. | Pilot deployed; UAT report prepared; known limitations documented; runbook shared. | Deployment decision: cloud, VPC or on-prem. | Containerized local/VPC deployment if production path pending. | Build team + Universal Sompo IT/RCU
Pilot Success Metrics
Metric | Target | How it is measured | Notes
Manual evidence search time | ≥70% reduction | Compare RCU baseline time vs tool-assisted time | Primary business case
Top-3 evidence precision | ≥80% | RCU marks if top-3 evidence links are relevant | After calibration
Audit trail coverage | 100% | Every output logs query, source, extracted field, score and correction | Non-negotiable
Auto-claim rejection | 0 | No final rejection decision automated | Human-in-loop only

## Workstream Matrix
Detailed Workstream Map — What Gets Completed By When
Organized around working software, not static documents.
Workstream | Week 1 | Week 2 | Week 3 | Week 4 | Completion Gate
Data + ingestion | Claim schema; Quest sample fields; mandatory field list. | FIR parser stable; OCR/text extraction tested. | Correction logs used in scoring; confidence thresholds active. | UAT fixes; final schema lock. | Validated claim object ready for scoring.
Search + sources | Vendor/API decision; source whitelist/blacklist. | Web/news/image queries live; async workers running. | Dedupe and source reliability tuning. | Quota/rate-limit settings finalized. | Top 10 ranked links with traceable source metadata.
Scoring logic | Weights drafted with RCU inputs. | Entity/date/location features tested. | Mismatch flags and score rationale live. | Thresholds calibrated against cases. | RCU can see why each result is ranked.
UI + output | Review screen wireframe. | Evidence list MVP with source tags. | Excel/PDF exports and case summary. | Final handover package. | Investigator-ready report exported.
Deployment | Cloud/VPC path confirmed. | Dev environment containerized. | Staging build and logging. | Pilot deployment and documentation. | Dockerized deployment package and runbook.

## Architecture Flow
Target Architecture — Retrieval + Ranking + Summarization
Async workers search in parallel, scoring stays explainable, and every output is traceable.
Layer / Component | Role in System | Stores / Processes | Key Dependency | Pilot Mode | Notes
Quest / FIR Docs | Primary case input source | Claim fields, FIR text/PDF, uploaded documents | Quest export/API/manual upload | CSV/manual upload fallback allowed | No pilot stall if Quest API is delayed.
Claim Fact Extractor | Converts raw FIR/Quest data into structured accident object | Date, time, location, vehicles, parties, cause, police station, district/state | OCR + LLM JSON extraction | Human review before search | Bad facts create garbage evidence; this is the first quality gate.
Query Generator | Creates multiple targeted search queries | Location/date/vehicle/victim/road accident Hindi/local variants | Claim object confidence | 5–8 queries per case | Search breadth matters for rural/local news.
Search Aggregator | Runs news/web/image searches in parallel | URLs, snippets, metadata, source, date, image matches | Search API vendor | Async workers + retries | Controls latency and API quota.
Evidence Extractor | Reads article/page metadata and relevant text | Title, source, publication date, body/snippet, image URL | Fetcher/parser reliability | Source whitelist/blacklist | Messy local pages need fallback snippets.
Scoring + Dashboard | Ranks evidence and shows mismatch flags | Relevance score, cause/date/location/entity flags, rationale | Weighted scoring rules + RCU calibration | Explainable scoring only | No black-box fraud decision.

## System Requirements
System Requirements — Pilot Default Configuration
Recommended first build is API-first. GPU is optional unless self-hosted AI is required inside the VPC.
Component | CPU / GPU | RAM | Storage | Purpose | Required for Pilot? | Notes
Application/API VM | 4 vCPU | 16 GB | 100 GB SSD | FastAPI, auth, dashboard backend, API orchestration, logging. | Yes | Ubuntu 22.04 + Docker.
PostgreSQL | 2–4 vCPU | 8–16 GB | Managed DB / SSD | Claim object, evidence metadata, scores, audit logs. | Yes | Can be managed cloud DB.
Redis | Shared / 1–2 vCPU | 2–4 GB | Small persistent / managed | Cache repeated searches, URL fetches, queue support. | Yes | Helps repeated investigations and latency.
Object Storage | N/A | N/A | 100–250 GB | FIR docs, evidence exports, PDF/Excel packs. | Yes | S3/GCS/Azure Blob or equivalent.
AI/OCR Layer — API-first | No dedicated GPU | N/A | N/A | Managed OCR/LLM or internal model endpoint for extraction, summary and embeddings. | Recommended default | Lowest operational complexity.
AI/OCR Layer — self-hosted | T4/L4/A10G GPU | 16–28 GB host RAM | 100 GB SSD | Self-hosted inference for extraction, embeddings and image similarity. | Conditional | Use only if data residency or procurement demands it.
Security Baseline | N/A | N/A | N/A | VPC/VPN access, encryption at rest, RBAC, PII redaction, full query-source audit trail. | Yes | Needed before UAT with real cases.
Pilot Sizing Assumption: 20–50 complaints/day, 3–5 concurrent investigators, 60–90 sec evidence turnaround target.

## GPU Cloud Cost
GPU & Cloud Cost — Pilot Month Scenarios
Rates are on-demand estimates from the deck. Final cost should be validated in the chosen cloud region before procurement.
Assumption | Value
FX rate USD to INR | 94.6
Testing hours / month | 160
Always-on hours / month | 730
API-first base monthly range | ₹40k–₹1.1L
Scenario | GPU | Typical Spec | USD/hr | INR/hr | Cost @160h | Cost @730h | Use | Decision
API-first pilot | No dedicated GPU | App + DB + Redis + storage + managed AI usage |  |  |  |  | Recommended default | Use first
AWS g4dn.xlarge | 1× NVIDIA T4 | 4 vCPU, 16 GB RAM | 0.526 | 49.7596 | 7961.536 | 36324.508 | Dev/UAT only | Use for dev/UAT
GCP g2-standard-4 | 1× NVIDIA L4 | 4 vCPU, 16 GB RAM | 0.707 | 66.8822 | 10701.152 | 48824.006 | Best self-host option | Use if self-hosting
AWS g5.xlarge | 1× NVIDIA A10G | 4 vCPU, 16 GB RAM | 1.006 | 95.1676 | 15226.816 | 69472.348 | Only if headroom needed | Use only if needed
Azure NC4as T4 v3 | 1× NVIDIA T4 | 4 vCPU, 28 GB RAM | 0.526 | 49.7596 | 7961.536 | 36324.508 | Azure/VPC preference | Use for Azure preference
Practical Recommendation
Start API-first. Add L4 only if data residency or procurement demands self-hosted models. Avoid H100/A100 capacity for this 4-week evidence-finder pilot because the workload is extraction, embeddings, ranking and light summarization, not large-model training.

## Scoring Model
Fraud-Risk Scoring — Explainable, Weighted, Evidence-First
The dashboard ranks evidence; it does not make final claim decisions.
Score Component | Weight | What it Checks | Example Signal | Owner of Calibration
Semantic similarity | 35% | How closely article/page content matches claim facts. | Same accident narrative, same district, same vehicle context. | AI/backend + RCU
Keyword / entity match | 20% | Vehicle number, names, police station, district, road, party details. | Vehicle number or victim name appears in public source. | RCU
Date proximity | 15% | Distance between FIR accident date/time and article publication/event date. | Article published near accident date. | RCU
Location feasibility | 15% | Whether public report/map structure aligns with FIR spot. | Road/spot/district match or conflict. | RCU + maps validation
Source reliability | 15% | Source reputation, recency, duplication, whitelist/blacklist rules. | Local news vs low-quality scraped page. | RCU + IT
Total Weight | 100%
Mismatch Flag | What gets surfaced
CAUSE | FIR and public evidence disagree on accident cause or direction of impact.
LOCATION | FIR spot not aligned with public report or map road structure.
TIME | Claim accident date/time is far from article timestamp or event date.
VEHICLE | Vehicle number/type absent or contradictory in public source.
ENTITY | Victim/driver names conflict with public source.

## Risks Decisions
Build Risks + Controls + Decisions Needed
Pilot risk is messy data, weak source availability and unclear integration ownership — not abstract model intelligence.
Risk / Decision Area | Risk or Required Decision | Control / Action | Deadline | Escalation Trigger
Sparse public data | Rural accidents may not have public articles. | Use multiple query variants, local-language terms, and mark “no public evidence found” without overclaiming. | W2 | Low source coverage across test cases.
Hindi/local news extraction | Messy pages and mixed-language reports reduce extraction quality. | Fallback to snippets + metadata; source whitelist/blacklist; manual reviewer note. | W2–W3 | Parser errors on repeated sources.
Search API latency/quota | Evidence search may become slow or costly. | Rate limiters, retry/backoff, Redis cache, vendor fallback. | W1 decision | Quota exhaustion or >90 sec response.
FIR OCR errors | Inconsistent PDF quality creates wrong claim facts. | Confidence scores, human review screen, correction logs. | W1–W2 | Mandatory fields below threshold.
False positives | Evidence treated as proof instead of lead. | Human-in-loop, rationale display, no auto-rejection, audit trail. | Always | Any final-decision automation request.
Quest integration mode | API/export/manual upload path must be confirmed. | Freeze API/export/manual path by Week 1; fallback to CSV/manual upload. | Day 5 | No access by W1 end.
Search API vendor | Vendor needs procurement/approval. | Approve one vendor for pilot; add others later. | Day 5 | Vendor not approved.
Deployment path | Cloud/VPC/on-prem needs IT confirmation. | Containerize app; keep VPC/on-prem compatible. | W1–W2 | No infra decision by W2.

## Definition of Done
Definition of Done — What Universal Sompo Receives After 4 Weeks
A usable pilot package, not only code snippets or a demo video.
No. | Deliverable | Description | Acceptance Evidence | Status | Notes
1 | Working pilot app | Case upload/input, fact review, evidence search, ranking, mismatch flags and investigator view. | Demo on 25–50 historical cases. | Planned
2 | Evidence exports | Excel/PDF pack with URL, source, date, relevance score, mismatch rationale and next verification step. | Export files generated from pilot app. | Planned
3 | Audit trail | Every query, source, extracted field, score and manual correction logged for review. | Audit table and sample trace shared. | Planned
4 | Deployment package | Dockerized backend, database schema, environment variables, runbook and handover notes. | Repo/package + deployment runbook. | Planned
5 | UAT report | Test case outcomes, ranking precision, known limitations, open issues and next build recommendations. | UAT report signed by reviewer. | Planned
Next phase after pilot: move to production only after source coverage, top-3 precision, privacy posture and Quest integration are proven. Scaling weak evidence retrieval will only automate noise.

## Source Notes
Source Notes + Assumptions
Workbook generated as a structured conversion of the Universal Sompo AI Claim Evidence Finder 4-week plan deck.
Assumption / Source | Value | Use
Input artifact | Universal_Sompo_4_Week_Build_and_GPU_Cost_Plan.pptx | Primary source deck converted into workbook
Reference artifact | Universal_Sompo_AI_Claim_Evidence_Finder_Tech_Plan(1).pptx | Earlier technical plan and scope reference
FX assumption | $1 ≈ ₹94.6 | Used for GPU compute conversion; update cell B5 on GPU Cloud Cost sheet if needed
GPU runtime assumption | 160h = start/stop testing; 730h = always-on monthly runtime | Used in formula-linked cost table
Cost limitation | Cloud pricing varies by region, commitment, taxes and negotiated enterprise rates | Validate before procurement